NGIN Alliance Playbook

Kickoff Call Agenda  +  Content Responsibility Matrix

February 23, 2026  ·  1:00 PM  ·  Jared (Pocketknife) & Taylor Dudley (NGIN)

1. Kickoff Call Agenda

Share this with Taylor before the call or use it to keep the conversation on track. The goal is to leave with every open question resolved and a clear set of next steps on both sides.

| Time | Topic | Lead | Notes / Key Questions |
| --- | --- | --- | --- |
| 0:00 – 0:05 | Intros & context | Jared | Brief overview of Pocketknife's role. Set a collaborative tone — position this as a partnership, not a vendor relationship. |
| 0:05 – 0:15 | Confirm: Microsite (RESOLVED) | Both | Confirm playbook.newgrowth.org as the build target. Briefly note the DNS access needed for subdomain setup in Phase 5. |
| 0:15 – 0:25 | Walk through updated timeline & milestones | Jared | Share the 7-week schedule (Feb 23 – Apr 13). Walk through each phase and its payment. Emphasize: each invoice must be paid before the next phase begins. Flag the 48-hr feedback expectation. |
| 0:25 – 0:35 | Review content map — confirm case study count & tool formats | Both | Walk through the site structure and content mapping. Key questions: How many case study pages total? Are the 15 tools meant to be downloadable files, web content, or both? Who preps the download files? |
| 0:35 – 0:45 | Confirm assets, access & communication norms | Both | Brand guidelines, logo files, photography. Squarespace account ownership. Google Analytics & Search Console access. Communication tool (email, Slack, PM tool). Feedback turnaround expectations. |
| 0:45 – 0:55 | Optional: Framework visuals add-on ($3,500) | Jared | If there's time, raise the optional infographics add-on for the Framework & Insights page. Not required today — can follow up in writing after the call. |
| 0:55 – 1:00 | Next steps & Phase 1 action items | Both | Confirm who does what before Feb 28. Send summary email after call. Agree on first check-in date. |

After the Call Send a recap email within 24 hours covering: confirmed decisions, open items, and Phase 1 action items with owners and due dates. Attach the updated timeline and content responsibility matrix so both parties have a shared reference from day one. If the framework visuals add-on was not discussed, follow up in writing within 48 hours — it's needed no later than start of Phase 2.

2. Content Responsibility Matrix

Every deliverable for the project, who owns it, when it's due, and any critical notes. Items marked NGIN are client dependencies — delays on these directly impact the April 13 go-live.

Color Key Pocketknife (green) = Pocketknife-owned deliverable NGIN (amber) = Client-owned deliverable — these are your watch items Most critical client deadlines: Brand assets by Feb 28 · All content by Mar 28 · DNS access by Apr 7

| Deliverable | Owner | Phase | Due By | Notes |
| --- | --- | --- | --- | --- |
| Kickoff call notes & recap email | Pocketknife | Phase 1 | Feb 23 | Jared sends summary within 24 hrs of call |
| Squarespace environment setup | Pocketknife | Phase 1 | Feb 28 |  |
| Sitemap draft for approval | Pocketknife | Phase 1 | Feb 28 | Client must approve before Phase 2 |
| Project management workspace | Pocketknife | Phase 1 | Feb 28 |  |
| Brand guidelines, logos & color palette | NGIN | Phase 1 | Feb 28 | Needed before design begins |
| Any existing photography / imagery | NGIN | Phase 1 | Feb 28 | Used in hero sections, case studies |
| Squarespace account access | NGIN | Phase 1 | Feb 28 | Confirm ownership; Pocketknife to be added as contributor |
| Design layouts for all page types | Pocketknife | Phase 2 | Mar 13 | Includes homepage, about, framework, resources, case study template |
| Design feedback — Round 1 | NGIN | Phase 2 | Mar 13+48h | 48-hour turnaround from design delivery |
| Design revisions | Pocketknife | Phase 2 | Mar 13+ |  |
| Framework visuals (if add-on approved) | Pocketknife | Phase 2 | Mar 13 | Optional $3,500 add-on. Confirm at kickoff. |
| All static pages built in Squarespace | Pocketknife | Phase 3 | Mar 28 | Home, About, Framework & Insights, Resources Bank, Cities Index |
| Case study template built & duplicated | Pocketknife | Phase 3 | Mar 28 | One template, applied to all confirmed case study pages |
| Finalized written content — all pages | NGIN | Phase 3 | Mar 28 | Text must be 100% final before Phase 4. Late content = at-risk go-live. |
| All case study content (text + data per city) | NGIN | Phase 3 | Mar 28 | Confirm total page count at kickoff |
| Tool files for Resources Bank (15 tools) | NGIN | Phase 3 | Mar 28 | PDFs or formatted Word docs ready for upload/download. Format TBD at kickoff. |
| Any additional imagery / headshots | NGIN | Phase 3 | Mar 28 |  |
| Content upload & formatting | Pocketknife | Phase 4 | Apr 4 | All client content must be in by Mar 28 |
| Content review — Round 2 | NGIN | Phase 4 | Apr 4+48h | Final opportunity to catch errors before QA |
| Content revisions | Pocketknife | Phase 4 | Apr 4+ | Scope changes at this stage billed at $150/hr |
| QA testing (devices & browsers) | Pocketknife | Phase 5 | Apr 7–13 |  |
| SEO setup (titles, alt text, URLs) | Pocketknife | Phase 5 | Apr 7–13 |  |
| DNS subdomain setup (playbook.newgrowth.org) | NGIN | Phase 5 | Apr 7 | Client must provide DNS access or make the change themselves. Allow 24–48 hrs for propagation. |
| Google Analytics & Search Console access | NGIN | Phase 5 | Apr 7 | Admin access needed before go-live |
| Final launch approval | NGIN | Phase 5 | Apr 13 | Written confirmation (email) required before go-live |
| Go-live & subdomain integration | Pocketknife | Phase 5 | Apr 13 |  |